## Slide 1: LipScribe Implementation Kick-off
Initial stand-up | Week 1 of 6 | 19 Oct – 29 Nov 2026
Computer Vision and Deep Learning | Group 4
Charis Opol
Coordinator & training
Cole Rodney Migisha
Model lead
Ainomugisha Faith
Data lead
Lisa Lusinga Namugenyi
Audio & evaluation
Wakisa Isabelle
Application lead
Ansasire Nehum Naamaye
QA & live systems
Notes: ~15 s. Welcome. This stand-up orients everyone on how we execute the implementation plan over the next six weeks. Everything here comes from the WBS in documentation/3_project_management, which is also what the Trello board is built from.

## Slide 2: What we must ship in six weeks
A live captioner that stays accurate in noise by reading the lips as well as listening.
4
core models
B1 audio · B2 visual B3 concat · P fusion
5
noise levels
clean, 10, 5, 0, −5 dB MUSAN noise
4
unseen test speakers
speaker-independent split, fixed in Week 1
<10%
WER target, clean
WER and CER at every SNR
Deliverables, due Sun 29 Nov
Trained models + configs & logs
Results tables from evaluate.py
Gradio demo + live captioning
Report, slides + demo video
Notes: ~1 min. The goal: a captioner that stays accurate when the audio is noisy, by fusing mouth video with audio. We train four core models: B1 audio-only, B2 visual-only, B3 simple concatenation, and P, our attention-plus-gate fusion with modality dropout. Every model is tested on four unseen speakers at five noise levels, clean down to minus 5 dB. Target: under 10% WER on clean audio; we report it honestly either way. The four deliverables at the bottom are what gets submitted on 29 Nov.

## Slide 3: Who owns what
Data pair
Ainomugisha Faith
Data lead
GRID download, integrity checks, splits, crop extraction, ablations
Lisa Lusinga Namugenyi
Audio & evaluation
MUSAN noise, mixing, tokeniser, evaluate.py, report editor
Model pair
Cole Rodney Migisha
Model lead
Mouth cropping, visual & audio encoders, attention fusion
Charis Opol
Coordinator & training
Trello, reviews, train.py, training runs, GPU booking
Application pair
Wakisa Isabelle
Application lead
Decoding, metrics, transcribe.py, Gradio demo, slides
Ansasire Nehum Naamaye
QA & live systems
Repo, environment, CI/tests, live mode, README
Notes: ~1 min. Six leads in three pairs. Your pair partner is your first reviewer. Data pair: Faith and Lisa. Model pair: Cole and Charis. Application pair: Isabelle and Nehum. This allocation balances workload; it is not based on known skills, so if you want to swap, say so today, before the board is finalised. Charis coordinates: Trello, weekly reviews, GPU booking and final submission.

## Slide 4: Six weeks, nine milestones
Week 1
19–25 Oct
M1
Setup & data
Env, GRID + MUSAN, integrity, splits.csv
Week 2
26 Oct–1 Nov
M2
Preprocessing
Crops cached, noise mixer, train.py, B1 starts
Week 3
2–8 Nov
M3 · M4
Baselines
B1, B2, B3 evaluated, beam search, demo v1
Week 4
9–15 Nov
M5
Fusion
Attention + gate model P, ablation configs
Week 5
16–22 Nov
M6 · M7 · M8
Tune & evaluate
Sweeps, final runs, ablations, live mode
Week 6
23–29 Nov
M8 · M9
Test & submit
Repro test, report, rehearsal, submission
Core freeze Sun 22 Nov · tag v1.0-core
Submission Sun 29 Nov · tag v1.0-final
Notes: ~1 min. One list per week on Trello, each closed by a milestone card reviewed on Sunday. Week 1 is set-up and data; week 2 preprocessing, and B1 starts training; week 3 the other baselines; week 4 the proposed fusion model; week 5 tuning, ablations, live demo, and the core freeze on Sun 22 Nov. After the freeze only bug fixes go into core code. Week 6 is testing, report and demo. Optional extensions only start after the freeze, and only if week 6 is on track.

## Slide 5: This week: setup and data
Mon 19
W1-01
Kick-off & board
Charis
Tue 20
W1-02
Repo skeleton
Nehum
Wed 21
W1-03
Pinned environment
Nehum
W1-04
GPU & storage
Charis
W1-05
Download GRID
Faith
Thu 22
W1-06
MUSAN noise pools
Lisa
W1-11
Interface spec
Isabelle
Fri 23
W1-07
Integrity checker
Faith
W1-09
Tokeniser
Lisa
W1-12
Tests & CI
Nehum
Sat 24
W1-08
Speaker split
Faith
W1-10
Mouth-crop prototype
Cole
Sun 25
M1
Milestone review
All
Critical path: GPU + storage → GRID download → integrity report → splits.csv (never regenerated)
Notes: ~1.5 min. Week 1 card by card, by due date. Read your own cards on Trello after this. The red path is critical: storage and GPU must be confirmed by Wednesday or the GRID download, the integrity report and the speaker split all slip, and everything in week 2 waits on splits.csv. If no GPU is confirmed by Wednesday, Charis escalates to the lecturer. Sunday is the M1 review: tests run for everyone, splits committed, GPU confirmed, crop prototype approved.

## Slide 6: How a card gets to Done
Week N
Card waits in its week list
In Progress
Owner starts the work
In Review
Pull request open
Done
Reviewer approves
Code
All code through a pull request; the reviewer approves
Every experiment has a committed YAML config
Never commit data, checkpoints or recordings
Never regenerate splits.csv after Week 1
Communication
Daily async update: done / doing / blocked
Weekly review, Friday, 1 hour
Blocked? Comment on the card and @Charis
Unfinished card moves on with a reason
Notes: ~45 s. Every card moves left to right. You move your card to In Progress when you start, to In Review when the pull request is open, and only the named reviewer moves it to Done. Rules on the right are on the REF-01 card. Two that bite if forgotten: never commit data, checkpoints or recordings, and never regenerate splits.csv after this week. Every result needs a committed YAML config, or it does not count.

## Slide 7: Risks and what we drop first
Risk | Mitigation
No GPU / disk | Confirm by Wed 21 Oct; escalate to lecturer
MediaPipe / Python mismatch | check_env.py on all six machines + GPU
Visual model learns slowly | Pre-train P's visual stream from B2 (W4-05)
Speaker leakage | One splits.csv + disjointness test
Fusion does not beat B1 | Diagnose and report it honestly
If we slip, drop in this order
1
Optional extensions
2
Experiments X4–X6
3
Live Mode B (keep Mode A)
4
Extra seeds
Never dropped
Baselines B1–B3 · proposed model P · per-SNR evaluation · ablations X1–X3
Notes: ~45 s. Biggest risk is compute: no GPU means no training, so it is settled this week. MediaPipe only ships wheels for some Python versions, so check_env.py runs on every machine first. If B2 learns slowly we initialise P's visual stream from B2. If the schedule slips we drop work in the order on the right. The four items at the bottom are never dropped; they are what the project is graded on.

## Slide 8: Before you leave today
1
Accept the Trello invite
Confirm your role and pair, or ask to swap now (W1-01)
2
Run check_env.py
Clone, pip install -e ., post the output on W1-03 by Wed
3
Report your GPU
Model and memory to Charis today, for the booking schedule (W1-04)
Next check-in: daily async update in the group chat · M1 review Sun 25 Oct
Notes: ~30 s. Three things from everyone. Accept the Trello invite and confirm your role, or raise a swap now. Clone the repo and run check_env.py once Nehum has pushed it, and post the output on card W1-03. Tell Charis today what GPU you have, if any. Then pick up your first card. Questions?

## Slide 9
Notes: Close. Take questions in the remaining time.